## Streamify Gantt Chart
Streamify Graduation Project - 9-Week Gantt Chart & Todo List
Task ID | Task Name | Phase | Start Week | End Week | Duration | Status | Progress | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9
T101 | Core Backend Server Setup & Architecture | Phase 1: Foundation | 1 | 2 | 2 | Completed | 100% | █ | █
T102 | Database Schema & Mongoose Architecture | Phase 1: Foundation | 1 | 2 | 2 | Completed | 100% | █ | █
T201 | User Auth Pipeline (JWT & Password Salting) | Phase 2: Core Logic | 2 | 3 | 1.5 | Completed | 100% |  | █ | █
T202 | Multi-stage Onboarding (Skills & Location) | Phase 2: Core Logic | 3 | 4 | 1 | Completed | 100% |  |  | █ | █
T203 | Isolated Relationship Tracker (FriendRequest) | Phase 2: Core Logic | 3 | 4 | 1 | Completed | 100% |  |  | █ | █
T204 | Stream.io SDK Token Generation & Signing | Phase 2: Core Logic | 4 | 4 | 0.5 | Completed | 100% |  |  |  | █
T205 | Automated Postman Integration Testing | Phase 2: Core Logic | 4 | 4 | 0.5 | Completed | 100% |  |  |  | █
T301 | Frontend Architecture Setup (React 19) | Phase 3: Client UI | 5 | 6 | 1.5 | In Progress | 15% |  |  |  |  | █ | █
T302 | TanStack Query Integration for Caching | Phase 3: Client UI | 6 | 7 | 1 | Planned | 0% | [5 empty] | █ | █
T303 | Interactive Dashboard & Stream SDK UI Chat | Phase 3: Client UI | 6 | 8 | 2 | Planned | 0% | [5 empty] | █ | █ | █
T401 | Docker Containerization (Dockerfile & WSL) | Phase 4: DevOps & Cloud | 8 | 9 | 1 | Planned | 0% | [7 empty] | █ | █
T402 | AWS Cloud Infrastructure Deployment | Phase 4: DevOps & Cloud | 9 | 9 | 1 | Planned | 0% | [8 empty] | █